## Sheet1
Task | Start Date | Days to complete
Start | 2023-09-13 | 1
Planning | 2023-09-13 | 10
Create basic HTML structure | 2023-09-24 | 3
Add CSS for structure | 2023-09-24 | 3
Create HTML Admin Panel for the website | 2023-09-30 | 4
Add JavaScript for Admin Panel | 2023-10-01 | 3
Add CSS FOR Admin Panel | 2023-10-02 | 2
Testing and Corrections | 2023-10-07 | 3
Creating Database | 2023-10-08 | 2
Link database to the website & testing | 2023-10-14 | 3
Run testing | 2023-10-21 | 3
Revision | 2023-10-28 | 2
Adding more features | 2023-10-31 | 1
Publish Admin Website | 2023-11-01 | 1
Testing With application | 2023-11-02 | 10
End | 2023-11-12 | 1